## Test Cases
Project Communications Plan
|  | Project Name: | AI-Powered Job Application Agent (No-Code SaaS Platform) |  | Date | 2025-09-19
Unique ID | Deliverable/Situation | Channel | Frequency | Upcoming Due Date | Owner | Internal Audience | External Audience | Purpose/ Agenda/ Content
1 | Project Kickoff | In-Person Meeting | One-Time | 2025-09-19 | Project Manager | Project Team | Project Sponsor (ZipRecruiter) | Introduct the project, confirm project objectives, goals, and deliverables
2 | Project Proposal | Virtual presentation + Email summary | One-time (Project initiation) | 2025-10-01 | Project Manager | Project Team, Technical Lead, Business Analyst | Project Sponsor (ZipRecruiter) | Present project scope, objectives, expected benefits, and approval for initiation
3 | Weekly Status | Team Stand-up (15 mins) + Weekly Email Report | Weekly | Every Thursday | Deputy Project Manager | Project Team (Dev, QA, UX, AI, BA) | N/A | Share weekly progress, blockers, completed tasks, and next week’s goals
4 | Customer Issue Escalation | Email escalation followed by Virtual meeting | As needed | Within 24 hours of issue | Project Manager | Technical Lead, QA Lead, BA | Sponsor PM, Customer Support Lead | Escalate high-impact issues affecting deliverables or customer satisfaction; agree on mitigation
5 | Monthly Cost & Schedule Review | Virtual Review Meeting + Dashboard Summary | Monthly | 1st Monday of each month | Project Manager | Technical Lead, BA, Deputy PM | Sponsor Finance Representative | Review project budget, resource utilization, and schedule adherence; approve corrective actions
6 | Interpersonal conflict within team members | One-on-one + Mediation Meeting (Private) | As needed | Within 2 days of incident | Project Manager / HR | Affected Team Members | HR Business Partner | Address conflict constructively, ensure team harmony, and agree on resolution actions
7 | Product Launch Announcement | Company-wide Townhall + Email + Social Media Post | One-time | 2026-06-30 | Project Manager | All Internal Staff | External Customers, Media, Partners | Announce final product release, highlight features, thank contributors, and communicate next steps
8
9
10