## Make or Buy Analysis
Make or Buy Analysis
|  | The Most Cost-Effective Option is: | MAKE
| Initial Costs | Ongoing Costs |  |  | TOTAL
Cost to Make | Initial | Q4 2025 | Q1 2026 | Q2 2026
Internal SME learning (200 hrs @ $60/hr) | 12000 | – | – | – | 12000
Internal BA/PM analysis time | 2000 | 2000 | – | – | 4000
Tools / research system cost | 500 | – | – | – | 500
Ongoing internal support | – | – | 2000 | 2000 | 4000
0
0
0
TOTAL | 14500 | 2000 | 2000 | 2000 | 20500
Cumulative Chart | 14500 | 16500 | 18500 | 20500
Cost to Buy | Initial | Q4 2025 | Q1 2026 | Q2 2026
HR Tech Consultant (150 hrs @ $150/hr) | 22500 | – | – | – | 22500
Compliance Advisor (100 hrs @ $150/hr) | 15000 | – | – | – | 15000
Vendor admin / onboarding costs | 2000 | – | – | – | 2000
Ongoing vendor consultation | – | – | 1500 | 1500 | 3000 | ◀ Insert more rows to add more costs. Copy the formulas and formatting from an existing row from above.
[5 empty] | 0 | ◀ Insert more columns to add more years (or weeks or months). Copy over an existing column to ensure the formulas carry over.
0
0
TOTAL | 39500 | 0 | 1500 | 1500 | 42500
Cumulative Chart | 39500 | 39500 | 41000 | 42500