## Project Charter
Project Charter
GENERAL PROJECT INFORMATION | CHARTER DATE: 19 September 2025
PROJECT NAME | AI-Powered Job Application Agent (No-Code SaaS Platform)
PROJECT SPONSOR | ZipRecruiter
PROJECT MANAGER | Nagalekha Ramesh
EXPECTED START DATE | 2025-10-01
EXPECTED COMPLETION DATE | 2025-06-30
PROJECT DETAILS
PROJECT DESCRIPTION | This project will deliver a no-code/low-code SaaS platform that enables an AI Agent to apply for jobs on behalf of users. It will provide a user-friendly interface that allows non-technical users to configure an agent that automates resume tailoring, job search, application submission, and tracking. The aim is to simplify and accelerate the job-seeking process while enhancing personalization and efficiency.
KEY REQUIREMENTS | The team will deliver these usable features in order: 1. No-code user interface for configuring an AI Agent. 2. Secure user authentication and profile management. 3. AI-powered resume and cover letter tailoring. 4. Automated integration with at least 3 job boards. 5. Smart job matching using user preferences. 6. Application tracking dashboard with notifications. 7. Compliance safeguards for data privacy.
EXPECTED BENEFITS | 1. Saves users significant time by automating repetitive job applications. 2. Improves application personalization, increasing chances of recruiter attention. 3. Enables non-technical users to configure advanced AI functionality with ease. 4. Provides an innovative solution in HR tech for job seekers.
ESTIMATED COST & RESOURCES | Approx. $700K - $750K for development, infrastructure, and integrations. Resources include: internal engineering team, UX/UI designer, QA testers, and compliance advisor.
ESTIMATED MILESTONES | Oct 15, 2025 – Project kickoff, requirements finalized. Nov 15, 2025 – Feature 1 & 2 completed: User interface + authentication. Dec 15, 2025 – Feature 3 completed: AI-powered resume & cover letter tailoring. Feb 1, 2026 – Feature 4 completed: Job board integrations (ZipRecruiter, LinkedIn, Indeed). Mar 15, 2026 – Feature 5 completed: Smart job matching & prioritization. Apr 15, 2026 – Feature 6 completed: Application tracking dashboard. May 15, 2026 – Feature 7 completed: Data privacy & compliance safeguards. Jun 10, 2026 – End-to-end testing and user acceptance. Jun 30, 2026 – Final release & project closure.
PROJECT TEAM (RESOURCES) | Project Sponsor: ZipRecruiter Project Manager: Nagalekha Ramesh Business Analysts: Rohaan Shaikh Senior Developers: Joevita Faustina Doss, Ketan Keshava, Rebecca Levin, Varun Gowda Test Lead: Alex Doe Subject Matter Experts: HR Tech Consultant, Compliance Advisor
STAKEHOLDERS (IMPACTED) | Job Seekers (primary users) Product & Engineering Teams Compliance/Legal Department Customer Support Team
OVERALL PROJECT RISK | Risk: Job board API access limitations. Likelihood: High, Impact: High. Risk: Data privacy non-compliance. Likelihood: Medium, Impact: High. Risk: AI-generated applications not meeting recruiter standards. Likelihood: Medium, Impact: High. Risk: Low adoption due to user trust concerns. Likelihood: Medium, Impact: Medium.
PROJECT EXIT CRITERIA | Working SaaS platform released by Jun 30, 2025. AI Agent applies successfully across 3 major job boards. Resume/cover letter tailoring validated by pilot users. Compliance review passed. Positive usability feedback from initial user group.