## Monthly Project Gantt Chart
[8 empty] | 2025-11-01 |  |  | 2026-02-01 |  |  | 2026-05-01 |  |  | 2026-08-01 |  |  | 2026-11-01 |  |  | 2027-02-01 |  |  | 2027-05-01 |  |  | 2027-08-01 |  |  | 2027-11-01 |  |  | 2028-02-01 |  |  | 2028-05-01 |  |  | 2028-08-01 |  |  | 2028-11-01 |  |  | 2029-02-01 |  |  | 2029-05-01 |  |  | 2029-08-01 |  |  | 2029-11-01 |  |  | 2030-02-01 |  |  | 2030-05-01 |  |  | 2030-08-01 |  |  | 2030-11-01 |  |  | 2031-02-01 |  |  | 2031-05-01 |  |  | 2031-08-01 |  |  | 2031-11-01 |  |  | 2032-02-01 |  |  | 2032-05-01 |  |  | 2032-08-01 |  |  | 2032-11-01 |  |  | 2033-02-01 |  |  | 2033-05-01 |  |  | 2033-08-01 |  |  | 2033-11-01 |  |  | 2034-02-01
| Project Start Date: | 2025-10-01 | [5 empty] | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1
| Project Name: | AI-Powered Job Application |  |  |  |  | Month: | time axis 2025-10-01 to 2034-04-08
# | Activity | Assigned To | Start | End | Days | Status | % Done
1 | Project Kick-off & Requirements Finalization | PM + BA | 2025-10-01 | 2025-10-15 | 11 | In progress | 10% | bar: 2025-10-01
2 | Design No-code UI (wireframes + mockups) | UX/UI | 2025-10-16 | 2025-11-05 | 15 | Not started | 0% | bar: 2025-11-01
3 | Implement No-code Workflow Builder | Dev Team | 2025-11-06 | 2025-11-25 | 14 | Not started | 0% | bar: 2025-11-01
4 | Backend Storage for Agent Settings | Dev Team | 2025-11-16 | 2025-11-30 | 10 | Not started | 0% | bar: 2025-11-01
5 | Secure Authentication (OAuth + MFA) | Dev Team | 2025-11-16 | 2025-12-15 | 21 | Not started | 0% | bar: 2025-12-01
6 | Profile Management | Dev + QA | 2025-12-01 | 2025-12-15 | 11 | Not started | 0% | bar: 2025-12-01
7 | AI Resume Tailoring | AI Dev + BA | 2025-12-01 | 2026-01-15 | 34 | Not started | 0% | bar: 2026-01-01
8 | AI Cover Letter Generation | AI Dev | 2026-01-16 | 2026-01-31 | 11 | Not started | 0% | bar: 2026-01-01
9 | Job Board API Research | BA | 2026-02-01 | 2026-02-10 | 7 | Not started | 0% | bar: 2026-02-01
10 | Job Board Integrations (ZipRecruiter, LinkedIn, Indeed) | Dev Team | 2026-02-11 | 2026-02-28 | 13 | Not started | 0% | bar: 2026-02-01
11 | Smart Job Matching Algorithm | Dev + AI | 2026-03-01 | 2026-03-15 | 10 | Not started | 0% | bar: 2026-03-01
12 | Pilot Testing for Matching | QA + Pilot Users | 2026-03-16 | 2026-03-31 | 12 | Not started | 0% | bar: 2026-03-01
13 | Application Tracking Dashboard (Design + Dev) | Dev + UX | 2026-04-01 | 2026-04-15 | 11 | Not started | 0% | bar: 2026-04-01
14 | Notifications & User Interaction Refinement | Dev + QA | 2026-04-16 | 2026-04-30 | 11 | Not started | 0% | bar: 2026-04-01
15 | Privacy & Compliance Review (GDPR/CCPA) | Compliance Advisor | 2026-05-01 | 2026-05-15 | 11 | Not started | 0% | bar: 2026-05-01
16 | Implement Data Privacy Safeguards | Dev + Compliance | 2026-05-16 | 2026-05-31 | 10 | Not started | 0% | bar: 2026-05-01
17 | End-to-End Testing & UAT | QA + All | 2026-06-01 | 2026-06-10 | 8 | Not started | 0% | bar: 2026-06-01
18 | Final Release & Project Closure | PM + Sponsor | 2026-06-11 | 2026-06-30 | 14 | Not started | 0% | bar: 2026-06-01
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Statuses
| Not started | ◄ Insert more rows to insert more statuses
In progress
Blocked
Complete
Quarter Names
| Q1 | Jan - Mar
| Q2 | Apr - Jun
| Q3 | Jul - Sep
| Q4 | Oct - Dec
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))
Enter the start month and delete this tip before you begin. The Calendar will start from the beginning of a Quarter.