## Test Cases
Project Work Breakdown Structure (Agile)
| Project Name: | AI-Powered Job Application Agent (No-Code SaaS Platform)
| Deliverable: | AI Job Agent
Unique ID | WBS Level | Breakdown
1 | Release 1 | Core Setup – No-Code Agent & Authentication
1.1 | Feature 1 | No-code Interface for Configuring Agent
1.1.1 | Story/Task 1 | Design wireframes and UI mockups
1.1.2 | Story/Task 2 | Implement drag-and-drop workflow builder
1.1.3 | Story/Task 3 | Develop backend storage for agent settings
1.2 | Feature 2 | Secure User Authentication & Profile Management
1.2.1 | Story/Task 1 | Integrate OAuth2 / SSO
1.2.2 | Story/Task 2 | Implement MFA (Multi-Factor Authentication)
1.2.3 | Story/Task 3 | Profile creation & session management
2 | Release 2 | AI Resume & Cover Letter Tailoring
2.1 | Feature 3 | Resume Tailoring via AI
2.1.1 | Story/Task 1 | Collect sample resumes & JDs for model testing
2.1.2 | Story/Task 2 | Integrate AI to suggest resume bullet edits
2.1.3 | Story/Task 3 | Build UI preview to compare before/after resume
2.2 | Feature 4 | Cover Letter Generation
2.2.1 | Story/Task 1 | Create cover letter templates
2.2.2 | Story/Task 2 | Integrate AI to draft letters based on job descriptions
2.2.3 | Story/Task 3 | Add review/edit functionality for user approval
3 | Release 3 | Job Board Integrations (Pilot Scope)
3.1 | Feature 5 | Integration with Job Boards (ZipRecruiter, LinkedIn, Indeed)
3.1.1 | Story/Task 1 | Research job board API availability
3.1.2 | Story/Task 2 | Build integration for job posting retrieval
3.1.3 | Story/Task 3 | Enable automated application submission
4 | Release 4 | Matching & Tracking
4.1 | Feature 6 | Smart Job Matching
4.1.1 | Story/Task 1 | Define matching algorithm using preferences
4.1.2 | Story/Task 2 | Test accuracy with pilot users
4.1.3 | Story/Task 3 | Optimize for speed and scale
4.2 | Feature 7 | Application Tracking Dashboard
4.2.1 | Story/Task 1 | Design dashboard layout
4.2.2 | Story/Task 2 | Add notifications for status updates
4.2.3 | Story/Task 3 | Test and refine user interactions
5 | Release 5 | Privacy & Compliance
5.1 | Feature 8 | Data Privacy Safeguards
5.1.1 | Story/Task 1 | Conduct GDPR/CCPA compliance review
5.1.2 | Story/Task 2 | Implement consent & data anonymization tools
5.1.3 | Story/Task 3 | Run compliance testing & finalize

## Sheet1
Unique ID | WBS Level | Breakdown
1.1.1 | Release 1 | Core Setup – No-Code Agent & Authentication
1.1.2 | Feature 1 | No-code Interface for Configuring Agent
1.1.1 | Story/Task 1 | Design wireframes and UI mockups
1.1.2 | Story/Task 2 | Implement drag-and-drop workflow builder
1.1.3 | Story/Task 3 | Develop backend storage for agent settings
1899-12-31 04:48 | Feature 2 | Secure User Authentication & Profile Management
1.2.1 | Story/Task 1 | Integrate OAuth2 / SSO
1.2.2 | Story/Task 2 | Implement MFA (Multi-Factor Authentication)
1.2.3 | Story/Task 3 | Profile creation & session management
1900-01-01 | Release 2 | AI Resume & Cover Letter Tailoring
1900-01-01 02:24 | Feature 3 | Resume Tailoring via AI
2.1.1 | Story/Task 1 | Collect sample resumes & JDs for model testing
2.1.2 | Story/Task 2 | Integrate AI to suggest resume bullet edits
2.1.3 | Story/Task 3 | Build UI preview to compare before/after resume
1900-01-01 04:48 | Feature 4 | Cover Letter Generation
2.2.1 | Story/Task 1 | Create cover letter templates
2.2.2 | Story/Task 2 | Integrate AI to draft letters based on job descriptions
2.2.3 | Story/Task 3 | Add review/edit functionality for user approval
1900-01-02 | Release 3 | Job Board Integrations (Pilot Scope)
3 | Feature 5 | Integration with Job Boards (ZipRecruiter, LinkedIn, Indeed)
3.1.1 | Story/Task 1 | Research job board API availability
3.1.2 | Story/Task 2 | Build integration for job posting retrieval
3.1.3 | Story/Task 3 | Enable automated application submission
1900-01-03 | Release 4 | Matching & Tracking
1900-01-03 02:24 | Feature 6 | Smart Job Matching
4.1.1 | Story/Task 1 | Define matching algorithm using preferences
4.1.2 | Story/Task 2 | Test accuracy with pilot users
4.1.3 | Story/Task 3 | Optimize for speed and scale
1900-01-03 04:48 | Feature 7 | Application Tracking Dashboard
4.2.1 | Story/Task 1 | Design dashboard layout
4.2.2 | Story/Task 2 | Add notifications for status updates
4.2.3 | Story/Task 3 | Test and refine user interactions
1900-01-04 | Release 5 | Privacy & Compliance
1900-01-04 02:24 | Feature 8 | Data Privacy Safeguards
5.1.1 | Story/Task 1 | Conduct GDPR/CCPA compliance review
5.1.2 | Story/Task 2 | Implement consent & data anonymization tools
5.1.3 | Story/Task 3 | Run compliance testing & finalize